## V1
Project Development and Completion Tracker
project id: TY AI 02
project start date:
project description: GenAI in Blender
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members | harkeerat dhunda | Team member | Project Development Student Team Memebers | Harkeerat Dhunda |  | complete | Project Domain Expert Team Members (Geolife) | harkeerat dhunda
| Vilakshan | Team member |  | Vilakshan |  | complete |  | Vilakshan
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Gathering models, data and papers for the genAI models and techniques | Data Collection | Complete | Harkeerat | 01-02-2024 | 20-02-2024 | 01-01-2024 | 10-02-2024 | 100%
|  | Data Collection | Complete | Vilakshan | 01-02-2024 | 20-02-2024 | 01-01-2024 | 10-02-2024 | 100%
Sprint 1 | Choosing the appropriate model and frontend | Model Selection | Complete | harkeerat, vilakshan | 01-03-2024 | 01-02-2024 | 01-02-2024 | 2024-02-15 | 100%
| Finetuning the model | Model Training | Complete | harkeerat, vilakshan | 01-02-2024 | 01-02-2024 | 01-02-2024 | 01-02-2024 | 100%
| Testing the model for different prompts | Model Evaluation | Complete | harkeerat, vilakshan | 01-02-2024 | 01-02-2024 | 01-02-2024 | 01-02-2024 | 100%